## Sheet1
SUMMARY OF RESOLUTION | MIN. No. | CMTEE | STRAT REF | MEETING DATE | RESPONSIBILITY | PROGRESS REPORT | Target Date | VALIDATION CHECK
Walking and Cycling Working Group | 2014/38 | EAC |  | 2014-06-25 | Ruth Knagg | No progress since last meeting. To be taken forward by Sarah Hobbs on her return in March. | 2014-10-22
Heart of Wessex Local Action Group | 2013/54 | EAC |  | 2013-06-26 | Peter Wheelhouse | A bid to DEFRA for £2 million has now been approved and potential project bids are being considered. A local Funding Advice Workshop was held on 10 Dec.
Garston Road play area | 2014/38 | EAC |  | 2014-06-25 | Paul Wynne | No progress since last meeting. Twon Clerk met with Bloor Hoems who were enthusiastic ion principle to explore if the s106 could be re-allocated. Town Clerk proposed to MDC on 16 Nov to meet up with Bloor and MDC to discuss but no response from MDC as yet.
Palmer Street resurfacing | 2013/74 | EAC |  | 2013-09-04 | Peter Wheelhouse | Following agreement with SCC on the components of a revised scheme, SCC have prepared a fresh design. An update on costings is expected imminently. We are working towards implementation in early 2015. | 2015-02-25
Apprenticeship programme | 2014/35 | EAC |  | 2014-06-25 | Peter Wheelhouse | Frome Community College is due to recruit an Apprenticeship Coordinator. This is taking longer than expected.
Foundry Barton and Henley Way | 2014/38 | EAC |  | 2014-06-25 | Paul Wynne | Acquisition proceeding. Awaiting action Persimmon Homes.
The Showfield | 2014/38 | EAC |  | 2014-06-25 | Paul Wynne | MDC agreed to surrender leases. Next step for FTC to acquire freehold and new lease from Agric Soc.
Cultural Quarter | 2014/47 | EAC |  | 2014-09-03 | Peter Wheelhouse | A bid for funding to enable a feasibility study to proceed has been lodged with the Arts Council.
Markets in Frome | 2014/46 | EAC |  | 2014-09-03 | Peter Wheelhouse | The idea of a perception survey now has the full support of Mendip District Council, the Frome Independent and the Cheese & Grain. A meeting with Cooper & Tanner to discuss the involvement of the Standerwick Market is due shortly. Work is proceeding to pull together survey questions. Full update at meeting on 25 February.
Community Database | 2014/51 | EAC |  | 2014-09-03 | Kate Hellard | In progress
Key
Overdue
On going (on schedule)
Action required
Upcoming item
Presentation planned
SUMMARY OF RESOLUTION | MINUTE NO. | CMTEE | STRAT REF | MEETING DATE | RESPONSIBILITY | PROGRESS REPORT | Target date | MINUTE NO. | CMTEE | STRAT REF
Implement Dog Control Orders | 2014/38 | IAC |  | 2014-10-08 | Tegwyn Jones | Tegwyn to insert update |  | 2014/38 | IAC
Recruit the Environment Manager | xxx |  |  |  |  | Inter views to be held on 24 Nov
Any accidents or other incidents related to health & safety since the last meeting (standing item) |  | IAC |  |  |  | On agenda |  |  | IAC
Appointment of Internal Auditors |  | IAC |  |  | Jackie Wheeler | On agenda |  |  | IAC
Plans for Christmas lighting |  | IAC |  |  | Allan Bennett | On agenda |  |  | IAC
Risk Register |  | IAC |  |  | Jackie Wheeler |  |  |  | IAC
Ethical Decision Making Matrix annual review | 2014/19 | IAC |  | 2014-04-09 | Jackie Wheeler |  |  | 2014/19 | IAC
Key | [6 empty] | Key
| Overdue | [6 empty] | Overdue
On going (on schedule)
Action required
SUMMARY OF RESOLUTION | MINUTE NO. | CMTEE | STRAT REF | MEETING DATE | RESPONSIBILITY | PROGRESS REPORT | Target Date
Frome Community Hub | 2014/40 | FC |  | 2014-05-21 | Paul Wynne | On the agenda | 2014-09-17
MDC plans for Local Legacy Grant Scheme for 2014/15 | 2013/57 | FC |  | 2013-07-24 | Paul Wynne | Applications have been submitted. We are expecting to hear back at the end of October | 2014-11-05
Frontier Estates application for development at Saxonvale |  | FC |  |  | Patrick Moss | The Frontier application remains to be determined and is not on the agenda for Mendip's Planning Board in September. Somerset County Council have not yet formally responded to the proposed highway alterations, involving an additional roundabout on Wesley Slope, but have indicated that they are unlikely to be acceptable.
Allocation of land supply for development in Frome | 2014/60 | FC |  | 2014-07-23 | Jane Llewellyn | Deadline for submission has now closed and we are awaiting feedback from MDC.
Market Place project | 2014/61 | FC |  | 2014-07-23 | Patrick Moss | Following discussions with the conservation officer for Mendip revised plans are being submitted that more closely follow the historic unobstructed views of the cross. These will be with Mendip Planning department next week. Discussions over land transfer and replacement free parking are progressing well.
Neighbourhood Plan |  | FC |  |  | Jane Llewellyn | This has been submitted and a discussion is planned for the next Council meeting. | 2014-11-05
Hustings |  | FC |  |  | Paul Wynne |  | 2014-11-05
Showfield |  | FC |  |  | Paul Wynne |  | 2014-11-05
External Auditors Report |  | FC |  |  | Jackie Wheeler
Precept Demand and agree Budget |  | FC |  |  | Jackie Wheeler |  | 2015-01-07
Sign off Work Programme |  | FC |  |  | Paul Wynne |  | 2015-01-07
Dispensation for Cllrs to vote on precept |  | FC |  |  | Paul Wynne |  | 2015-01-07
Review of financial regulations and committee terms of reference |  | FC |  |  | Jackie Wheeler |  | 2015-01-07
Annual Return |  | FC |  |  | Jackie Wheeler |  | 2015-05-20
Sole managing trustee meetings |  | FC |  |  | Paul Wynne |  | 2015-07-01
Annual Report |  | FC |  |  | Paul Wynne |  | 2015-07-01
Key
Overdue
On going (on schedule)
Action required
Upcoming item
Presentation planned