## Sheet1
SUMMARY OF RESOLUTION | MINUTE NO. | CMTEE | STRAT REF | MEETING DATE | RESPONSIBILITY | PROGRESS REPORT | Target Date | VALIDATION CHECK
List of community organisations involved with the Community Fair in 2012 publicised | 2012/70 | EAC |  | 2012-09-19 | Comm Project Off | To be taken over by the Community Projects Officer | Spring 2013 | OK
Return of produce market on a Wednesday | 2012/68 | EAC |  | 2012-09-19 | Peter Wheelhouse | Karen has had an initial conversation with Quintyn at Cooper & Tanner. Further research is now required. | On-going | OK
Walking and Cycling Working Group | 2014/38 | EAC |  | 2014-06-25 | Ruth Knagg | On agenda | 2014-10-22
Heart of Wessex Local Action Group | 2013/54 | EAC |  | 2013-06-26 | Peter Wheelhouse | A bid to DEFRA for £2 million has now been submitted. This follows work on a Local Development Strategy that the ERDM contributed to. We expect to hear the result of the bid in late November but in the meantime a local Funding Advice Workshop will be arranged.
Open Spaces | 2014/38 | EAC |  | 2014-06-25 | Ruth Knagg | On agenda | 2014-10-22
Garston Road play area | 2014/38 | EAC |  | 2014-06-25 | Paul Wynne | No progress since last meeting.
Palmer Street resurfacing | 2013/74 | EAC |  | 2013-09-04 | Peter Wheelhouse | Following agreement with SCC on the components of a revised scheme, SCC have prepared a fresh design. An update on costings is expected imminently. We are working towards implementation in early 2015. | 2015-02-25
Riverside Project (Henley Way/Welshmill Lane) | 2014/38 | EAC |  | 2014-06-25 | Ruth Knagg | On agenda | 2014-10-22
Apprenticeship programme | 2014/35 | EAC |  | 2014-06-25 | Peter Wheelhouse | Frome Community College is due to recruit an Apprenticeship Coordinator imminently.
Foundry Barton and Henley Way | 2014/38 | EAC |  | 2014-06-25 | Paul Wynne | Acquisition proceeding. Awaiting action from MDC.
The Showfield | 2014/38 | EAC |  | 2014-06-25 | Paul Wynne | Discussions with Agricultural Society are on-going over the acquisition, meanwhile on site improvements funded by the s106 agreement are on hold
Cultural Quarter | 2014/47 | EAC |  | 2014-09-03 | Peter Wheelhouse | A bid for funding to enable a feasibility study to proceed has been lodged with the Arts Council.
Markets in Frome | 2014/46 | EAC |  | 2014-09-03 | Peter Wheelhouse | The idea of a perception survey now has the full support of Mendip District Council, the Frome Independent and the Cheese & Grain. A meeting with Cooper & Tanner to discuss the involvement of the Standerwick Market is due shortly. Work is proceeding to pull together survey questions.
Community Database | 2014/51 | EAC |  | 2014-09-03 | Kate Hellard | On agenda | 2014-10-22
Review of Greenstrand support | 2014/24 | EAC |  | 2014-04-30 | Paul Wynne | On agenda | 2014-10-22
Car Club |  | EAC |  |  | Anna Francis |  | 2014-12-17
Participate Frome |  | EAC |  |  | Kate Hellard |  | 2014-12-17
To consider next years work programme |  | EAC |  |  | Jackie Wheeler |  | 2014-12-17
Parking Strategy |  | EAC |  |  | Patrick Moss |  | 2014-12-17
Community Grants |  | EAC |  |  | Ruth Knagg |  | 2014-02-25
Key
Overdue
On going (on schedule)
Action required
Upcoming item
Presentation planned
SUMMARY OF RESOLUTION | MINUTE NO. | CMTEE | STRAT REF | MEETING DATE | RESPONSIBILITY | PROGRESS REPORT | Target Date
Dog control orders | 2014/38 | IAC |  | 2014-06-11 | Paul Wynne | On agenda | 2014-10-08
s106 expenditure | 2014/34 | IAC |  | 11/6/14 | Jackie Wheeler | The s106 agreement for the MUGA has been transferred from MDC to FTC.
Improving the infrastructure to support tourism | 2014/37 | IAC |  | 11/6/14 | Peter Wheelhouse | Work is in progress on the development of a signage and landscaping scheme for the Market Yard. There have also been discussions with some of the venues around the Market Yard and the Senior Economic Development Officer at Mendip District Council. Those discussions relate to the design of a feasibility study to consider how this space can develop as an arrival point and cultural destination. Arts Council funding is currently being sought to enable this feasibility study to proceed.
Any accidents or other incidents related to health & safety since the last meeting (standing item) |  | IAC |  |  |  | On agenda | 2014-10-08
Appointment of Internal Auditors |  | IAC |  |  | Jackie Wheeler | On agenda | 2014-10-08
Plans for Christmas lighting |  | IAC |  |  | Allan Bennett | On agenda | 2014-10-08
Discussion on next year's work programme and budget |  | IAC |  |  | Jackie Wheeler |  | 2014-12-02
Risk Register |  | IAC |  |  | Jackie Wheeler |  | 2015-02-03
Ethical Decision Making Matrix annual review | 2014/19 | IAC |  | 2014-04-09 | Jackie Wheeler |  | 2015-04-08
Key
Overdue
On going (on schedule)
Action required
SUMMARY OF RESOLUTION | MINUTE NO. | CMTEE | STRAT REF | MEETING DATE | RESPONSIBILITY | PROGRESS REPORT | Target Date
Frome Community Hub | 2014/40 | FC |  | 2014-05-21 | Paul Wynne | On the agenda
MDC plans for Local Legacy Grant Scheme for 2014/15 | 2013/57 | FC |  | 2013-07-24 | Paul Wynne | On the agenda
Frontier Estates application for development at Saxonvale |  | FC |  |  | Patrick Moss | The Frontier application remains undetermined and will not be the agenda for Mendip's Planning Board before Christmas. Somerset County Council have not yet formally responded to the proposed highway alterations, involving an additional roundabout on Wesley Slope, but have indicated that they are unlikely to be acceptable.
Market Place project | 2014/61 | FC |  | 2014-07-23 | Patrick Moss | Following further discussions with Mendip's Conservation Officer and other stakeholders, consultants IMA and Nicholas Pearson Associates have been working on some further revisions to the original design. Mendip District Council will consider these revisions, our request for a transfer of the land and our proposals for replacement free parking as soon as revisions are completed.
Neighbourhood Plan |  | FC |  |  | Jane Llewellyn | On the agenda
Precept Demand and agree Budget |  | FC |  |  | Jackie Wheeler |  | 2015-01-07
Sign off Work Programme |  | FC |  |  | Paul Wynne |  | 2015-01-07
Dispensation for Cllrs to vote on precept |  | FC |  |  | Paul Wynne |  | 2015-01-07
Review of financial regulations and committee terms of reference |  | FC |  |  | Jackie Wheeler |  | 2015-01-07
Annual Return |  | FC |  |  | Jackie Wheeler |  | 2015-05-20
Sole managing trustee meetings |  | FC |  |  | Paul Wynne |  | 2015-07-01
Annual Report |  | FC |  |  | Paul Wynne |  | 2015-07-01
Key
Overdue
On going (on schedule)
Action required
Upcoming item
Presentation planned