## Sheet1
FROME TOWN COUNCIL - STRATEGIC PLAN
APPENDIX 2
ACTION PLAN - DECEMBER 2011 to MARCH 2016
1. | Encouraging a Dynamic and Sustainable Economy
| 1.1 | Economic Development
Budget cost
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16 | centre & code
|  | 1.1.1 | Develop a sustainable economy for Frome | EAC / EDRM | 2012/13 & 2013/14
|  |  | Develop an economic development plan to include: | EAC / EDRM | April 2013 | On target | Focused on specific projects rather than writing a report | Focus for 2015/16 will be on implementing the policies in the Neighbourhood Plan, identification of work space and green technology. Research into demand for workspace to be published in early 2015.We will then work to bring forward new workspace on sites identified within the Neighbourhood Plan and work to develop a cluster of environmental technology businesses under the banner of 'One Planet Valley' at Saxonvale. | 506 4128
|  |  | Oversee and help co-ordinate all activities in the town centre including Town Team projects: Frome App, Super Market and Keep Frome Clean | EAC / EDRM | Ongoing | Frome App online by April 2013; Keep Frome Clean project in development; successful Frome Super Market pilot | Ongoing | Frome Independent market has developed well. In 2015/16 we will complete phase 1 of Market Place remodelling; improve the Market Yard; improve signage between the town centre and the station; develop further the new websites with town centre information and establish a Town Centre Working Group to work with the community and businesses to enhance the town centre further. This group will: improve information and signage for pedestrians, cyclists and drivers; better promote and expand the Community Toilet Scheme; improve street cleanliness; improve sustainable transport services; establish a car park regime that encourages people to use the town centre and developing markets and events.
|  |  | Establish and develop network involving Frome Chamber of Commerce, local businesses, Heart of SW Local Enterprise Partnership (LEP), Somerset County Council, Mendip District Council, BANES, Wiltshire Council, and other stakeholders | EAC / EDRM | Ongoing | Network well established | Ongoing | Ongoing
|  | 1.1.2 | Research/data gathering to support economic and community development work | EAC /CPO/ERDM | 2013/14 | New project | Business database purchased, community database to be part of new website | Community Groups Database is developed and will be incorporated into websites. | 506 4122
| 1.2 | Boost the identity of the town
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 1.2.1 | Use local and national expertise to create a unique identity for the town and find new ways of effectively marketing that identity | EAC / EDRM | Ongoing |  |  |  | 506 4128
|  |  | Produce and implement a marketing strategy for the town - to include: | EAC / EDRM
|  |  | Improve FTC website linked to 'Frome Fizz' - a new cultural and community portal for Frome | EAC / EDRM | 2013/14 | New project | New website to be launched in February 2014 | Websites completed and continual improvements needed | 802 4027
|  |  | Develop 'Welcome Pack' for investors, visitors and people moving to the town | EAC / EDRM |  | New project | Do not progress | New project - online and paper resource
|  |  | Work with 'Into Somerset' and Heart of the SW LEP to improve awareness of Frome as a business location and generate leads | EAC / EDRM | 2013/14 | Contacts established | Ongoing project | Good progress with LEP and SMT event. Next step is development of a prospectus for the town to set out Frome's offer to new businesses
|  |  | Work with venues, festival organisers and accommodation providers to promote the town to visitors | EAC / EDRM | 2013/14 | Discussions proceeding with partners | part of website project | Discover Frome website up and running. We will contnue to promte Frome via a targetted media campaign; continue to work with Bath and Bristol as potential 'gateways' for international visitors; explore further potential of tour operaators to bring tourists to Frome for the day; promotion planned with First Great Western & Heart of Wessex Community Rail Partnership to promote visits by rail
|  |  | Support production of town maps promoting pedestrian routes | EAC / ERO | April 2013 | On target | In progress | Will be developed further to promote sustainable transport including walking
| 1.3 | Help the local economy become resilient, self reliant and sustainable
(see 2.4)
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013
|  | 3.3.7 | Investigate options for electric powered vehicle for FTC run services | TC | June 2012 | Completed |  | Replace diesel van in 2015/16 | EMR 901 9008
| 1.4 | Assist the unemployed, under-employed and school leavers
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 1.4.1 | Work with local entrepreneurs, educational establishments and other training providers to identify and meet skill needs in the town (to include enhanced HE and FE provision) | EAC/ERDM | 2014/5 | Safeguarded training operations at Saxonvale Centre | Training/Apprentice Academy plan in progress | Apprenticeship Coordinator funded by FTC to be appointed by end of Dec 2015. Main focus through to March 2016 will be to work with employers to create new apprenticeship opportunities for local young people in the town. | EMR 901 9023
|  | 1.3.2 | Investigate opportunity for development of 'green collar' skills to support green retrofit and renewable energy production. | EAC/ERDM | 2014/15 | New project | New project | Project in implementation stage | EMR 901 9023
|  | 1.4.2 | Work with partners to improve the availability of help for the unemployed | EAC / ERDM | Ongoing | Contact made with Somerset County Council, Jobcentre Plus, Careers SW, Frome Community College and Edventure to identify what more can be done to support unemployed | See 1.4.1 above | See 1.4.1 above | EMR 901 9023
|  | 1.4.3 | Facilitate business start ups, training and sharing knowledge | EAC / ERDM
|  |  | Support creative business sector | EAC / ERDM | April 2013 | Sector supported through funding for Frome App project (Somerset County Council and FTC) |  | Chairing Cultural Quarter working group. Feasibility study grant application submitted - link with public realm improvements to Market Yard | EMR 901 9023
|  |  | Provide information on available premises and sources of business support on FTC website | EAC/ERDM | 2014/15 | New project | On new website | Completed needs to be kep up to date | 802 4027
|  |  | Safeguard sites that are suitable for small businesses, encourage development of new incubation space and enable small businesses to be established in the town centre through new planning policies (Neighbourhood Plan) | EAC/PDO | 2014/15 | Work in progress on Neighbourhood Plan, see 2.3.3 below |  | NP complete and study of business sites commissioned. See also 1.1.1 above | 506 4129
|  |  | Work with Frome Community College to develop their new 'Nurture Centre' | EAC/ERDM | 2014/15 | Discussions ongoing with Frome Community College | See 1.4.1 above | See 1.4.1 above | EMR 901 9023
|  | 2.5.3 | Explore opportunities for a University of Somerset campus | EAC/EDRM | 2013/14 | See also 1.4.1 | Do not progress
2. | Creating a Vibrant Participatory Community
| 2.1 | Encourage community groups to take the lead
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 2.1.1 | Extend the capacity of FTC's grant budget | EAC / CPO | 2014/15 | Completed | Grant review in progress | Grant scheme reviewed and is now more focussed. Some of the previous grant fund re-directed to supporting group development | 503 4720
|  | 2.1.2 | Introduce Participatory Budgeting for community grants | EAC / RFO | April 2012 | Completed |  | Focus more on supporting group development. Consider formal participatory budgeting project in advance of 2016/17 budget.
|  | 2.1.3 | Investigate provision of umbrella services for community groups i.e. insurance, storage and accountancy | IAC/RFO | 2014/15 | Not possible via FTC insurance policy, cheap individual cover for groups available | Investigate capacity on already providing accountancy services for car club | Discount scheme arranged with an insurance company if community groups quote FTC
|  | 2.5.2 | Work in partnership with the Cheese & Grain (C&G) trust to ensure it has a clear strategy for the future, is able to function as a viable organisation and continues to provide a valuable community service | IAC/TC | 2013 |  |  | ongoing
|  |  | Support C&G in their renewable energy project | IAC/ERO | March 2012 | Completed | Completed | Completed
|  |  | Put in place a new sustainable Service Level Agreement (SLA) | IAC/TC | March 2012 | Completed | Completed | Completed
|  |  | Work with C&G to develop Mezzanine and Tower to create viable income stream | IAC/EDRM | 2013/14 | Project to develop Mezzanine and Tower in progress | Mezzanine project complete Nov 2013 | Tower project in planning stage
| 2.2 | Make best use of town's green spaces
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 2.2.1 | Develop a town-wide Strategy for open spaces and play facilities | IAC / EM | February 2012 | Completed | Review of Strategy in Nov/Dec 2013 | Acquisition of Dippy, Old Showfield, Play Park at Henley Way, riverbank in town centre and promotion of community purchase of Whatcombe Fields in progress. Open Spaces Strategy to be reviewed winter 2014/5 and the Save Open Spaces research on protecting land incorporated. To be progressed by Env Manager.
|  |  | Mapping of all green spaces and walkways including corridors of diversity | IAC / CPO | July 2013 |  | Completed, to be incorporated into review of Open Spaces | Green infrastructure / Green Space network to be taken forward by Environment Manager. | EMR 901 9010
|  |  | Investigate sources of external funding | IAC / CPO | 2014/15 |  | MUGA grant to be applied for and support for Tennis Court bid | Sport England grant aided MUGA (in construction) and new tennis courts (to be completed by end Summer 2015)
|  |  | Explore innovative ways of protecting open spaces e.g. Queen Elizabeth 2 Fields Challenge and asset transfer | IAC / CPO | 2013/14 | Asset transfer from MDC to FTC priority sites from Strategy, sites placed on asset register | Supporting FROGS to apply for Village Green, Asset of Comm Value etc | Save open Spaces produced study of best methods of protection which will inform review of Open Spaces strategy
|  |  | Identify potential land for acquisition by FTC | FC/TC | 2013/14 | sites identified in Strategy, acquisition from MDC ongoing | Dippy, Showfield and North Parade to be transferred in 2014 | the Old Showfield, the Dippy, land at North Parade, land at Henley Way will be acquired by end March 2015.
|  |  | Investigate other uses of closed churchyards | IAC/EM | 2013/14 | will discuss with new contractors re management and MDC re acquisition | Do not progress | To be progressed by Env Manager
|  |  | Support community natural play project at Welshmill | IAC/GPM | 2013/14 | Phase 1 completed, phase 2 & 3 start Spring 2013 | Phase 2 in progress | Phase 3 to be started in 2015/16 | 505 4902
|  | 2.2.2 | Improve skate and bike facilities across town | IAC / EM
|  |  | Support community led skate park project | IAC / EM | June 2012 | Completed | completed | completed
|  |  | Support community led pump track project at Welshmill | IAC / EM | June 2012 | Completed | completed | completed
|  | 2.2.3 | Promote the river through enhancement works | IAC / EM
|  |  | Create and implement a river enhancement project (incorporating possible hydro unit at Welshmill) | IAC / EM | 2013/14/15 | Project plan completed, detailed design started, NHB funding in negotiation | NHB secured for Henley Way footpath only. Rodden Meadow to be completed 2014. Market Yard improvements not funded | Next phase of strategy is to: build a bridge across river to Rodden Meadow funded mostly by s106; signage and promotion of river corridor access routes; complete works at Rodden Meadow, explore acquisition of fields beyond the Mount towards the by-pass. | 506 4136 + S106 EMR 901 9039
|  | 2.2.4 | Promote increased tree planting | IAC / EM |  |  | Do not progress | To be progressed by Env Manager with More Trees Frome coordinator and part of green infrastructure project | 504 4908
|  |  | Identify public areas for the provision of trees | IAC / EM | 2013/14 | New project | Do not progress | as above
|  |  | Consider options for planting in residential areas and urban landscapes | IAC / EM | 2013/14 | New project | Do not progress | as above
|  | 2.2.5 | Support and promote the work of community groups with shared aims | EAC/CPO | 2014/15 |  | Participation Week completed Nov 2013 - planning for next steps | Excellent engagement projects completed over the year and more resources will be put in to develop enagagement and volunteering in 2015/16 | 503 4720
| 2.3 | Maintain the town character whilst encouraging sustainable growth
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 2.3.1 | Develop Town Design Statement for adoption by the Planning Authority | EAC / PDO | August 2012 | Completed and passed to MDC for approval |  | Awaiting MDC approval still
|  | 2.3.2 | Lobby for direct access to New Homes Bonus and Community Infrastructure Levy and Business Rates to support the local infrastructure in Frome | FC / TC | 2014/15 | Negotiating with MDC to fund River Corridor and Market Place projects | NHB secured for Henley Way path but no other funding forthcoming | No progress to date over more control over NHB, establishing CIL. We will continue to push for this and for rates relief on some businesses and a premuim on business rates to pay for improvements.
|  | 2.3.3 | Develop Neighbourhood Development Plan for adoption by the Planning Authority | EAC / PDO | 2014 | On schedule | Consultation in progress, Plan to be submitted to MDC Spring 2014 | Plan submitted Summer 2014; may need to amend following inspection. | 506 4129
|  |  | Ensure new developments include long term job opportunities | EAC / PDO |  | In progress |  | Once adopted the plan will form basis of advocacy work to promote/enforce policies.
|  |  | Ensure existing employment land is safeguarded | EAC / PDO |  | In progress |  | Once adopted the plan will form basis of advocacy work to promote/enforce policies.
|  |  | Protect green open spaces | EAC / PDO |  | In progress |  | Once adopted the plan will form basis of advocacy work to promote/enforce policies.
|  |  | Claim the right to make planning decisions through Local Development Order | EAC / PDO |  | In progress |  | Exploring as part of Saxonvale Investment Prospectus project
|  | 2.3.4 | Once adopted publicise the Plan and secure implementation | EAC/PDO | 2014/15 | Next phase of project | Next phase of project | Once adopted the plan will form basis of advocacy work to promote/enforce policies. | 506 4129
| 2.4 | Help the local householders become resilient, self reliant and sustainable
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 2.4.1 | Work in partnership with the Frome Development Community Interest Company to provide more allotment and community garden space | IAC/EM | Oct. 2012 | Birchill lane open spaces acquired |  | Possibility of more allotments at Whatcombe fields if community purchase campaign successful
|  | 2.4.2 | Support new developments with good eco and climate credentials | EAC / PDO | 2014 onwards |  | Need to recommend higher insulation and energy standards in applns | Intensify work on promoting good applications and highlighting bad ones
|  |  | Carry out Carbon Audit | EAC/ERO | 2013/14 | New project | Completed - Converging World | completed
|  | 2.4.3 | Lobby for an increase in recycling provision |  |  |  |  | Good relationship with Somerset Waste Partnership established - exploring opportunities around re-use and recycling. VHS recycling programme launched
|  |  | Work in partnership with Somerset County Council (SCC) to extend opening hours of the recycling centre | TC / SCC | 2012/13 | Too expensive |  | Recycling Centre hours now extended
|  |  | Develop an initiative with businesses to eliminate use of plastic shopping bags | EAC/ERO | 2014/15 | New project | New project | Do not progress - bag tax being introduced nationally in May 2015. Recycled Frome bag launched | 503 4719
|  |  | Work in partnership with local businesses to provide multi use recycling bins within the town centre | EAC/ERO | 2014/15 | New project | New project | new project.Focus in 2015/16 will be working with businesses to reduce carbon footprint and imprve public realm | 503 4719
|  |  | Work with the community to increase knowledge levels about importance and opportunities of recycling/re-use and about destination of waste and recycled materials | EAC/ERO | 2014/15 | New project | New project | Working with Protomax to recycle plastic and manufacture planters and benches for Frome and with schools to highlight potetnial of re-use and recycling | 503 4719
|  | 2.4.4 | Work in partnership with Sustainable Frome to provide a consortium for centralised purchasing with energy providers and renewable sourced products | EAC/ERO | 2014/15 | New project | New project | MDC launched a scheme which we are promoting. FTC/Frome Renewable Energy Co-op exploring becoming a local energy provider. | 503 4719
|  | 2.4.5 | Investigate opportunities for subsidised insulation, sustainable home improvements and the re-use/reduction of waste | EAC/ERO | 2014/15 | New project | New project | We will: continue to promote grants, information and subsidies; develop our team of 6 energy volunteers that runs energy advice sessions; launch a thermal imaging and bulk buy of energy saving products in early 2015; loan LED kits and energy monitors through the library; continue our School Carbon Countdown programme that was launched in October; promote electric charge points that have been installed at the Cheese and Grain; continue to work on a sustainable transport programme encompassing Frome and surrounding area, including re-modelling of the railway station and subsidised cycle training | 503 4719
|  |  | Engage with 'Transitional Streets' initiative | EAC/ERO | 2014/15 | see also 1.3.1 | New project | Do not progress
| 2.5 | Build on the range of facilities and activities available locally
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 2.5.1 | Encourage sports clubs and organisations to work together to share facilities and costs | EAC/CPO | August 2012 | Working party established, next steps behind schedule | Meetings held no further action apart from supporting tennis courts, MUGA. | no further work on sport club development | 901 9006
|  |  | Set up organisations day to promote awareness between groups and local people | EAC/CPO | March 2012 | Annual community fair 2013 in planning stage | Participate Frome held in November 2013 | Ongoing projects on youth groups, cultural quarter, green energy groups, support for older people lacking. We are looking to the new building to provide opportunity for increased information sharing and will build on the work to date on the Community Website. | 503 4723
|  |  | Assist and encourage all schools (state, academic or free) in using local sports and theatre facilities | EAC/CPO | 2011/12 | Behind schedule | Do not progress | Do not progress
| 2.6 | Support the town's arts scene
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 2.6.1 | Encourage arts organisations to work together to share facilities and costs | EAC/EDRM |  |  |  | Contiue to wrok on Cultrual Quarter Projecet
|  |  | Work in partnership with arts organisation to investigate shared marketing and box office functions |  | 2012/13 | Creative Frome taking forward |  | Cheese and Grain taking forward
|  | 2.6.2 | Provide assistance with large scale events | EAC/EDRM | 2014/15 |  | Christmas Extravaganza event planned for Nov 2013, annual event | Festival, Carnival and Extravaganza have been and will continue to be supported. | 502 4320 4325 4333
|  |  | Investigate general public liability insurance for council supported events | EAC/RFO | Oct. 2012 | Support given where possible | No umbrella insurance available via FTC. | No umbrella insurance available via FTC.
|  |  | Help facilitate events with resources, project management expertise, use of land and fundraising etc | EAC/EDRM | Annual | Support given where possible | Carnival, Festival and Cobble Wobble all supported | Festival, Carnival and Extravaganza supported. | 502 4320 4325
| 2.7 | Community involvement
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 2.7.1 | Explore and encourage community engagement | EAC/TC | 2014/15 |  |  | Participate Frome agenda being developed to ensure that communication is addressed at a basic level and will then developed to facilitate engagement. The Hub will create base for engagement and communication. Democracy Day planned for April 2015. | 503 4720 501 4018
|  |  | Facilitate debates on the future of education in Frome | TC/Cllr Usher | Nov 2012 | Nov FC - presentations from College and Steiner Schools. See also 4.1 |  | do not progress
|  |  | Facilitate public Question Time so that the public have access to elected officials across all public services | EAC/Cllr Godman | Ongoing | 2 QTs already held |  | do not progress
|  |  | Create a Citizens Jury to review evidence on the development of Saxonvale | EAC/EDRM | 2013/14 | New project when time is right | One public debate held, second planned for Feb 2014 | Following the publication of the Saxonvale Prospectus the work of enagging the commnuity will be rekindled. | 501 4018
|  |  | Public Referenda on Neighbourhood Planning | FC/PDO | 2014 | On schedule |  | Referendum to be held in May 2015
|  | 2.7.2 | Encourage and support participatory projects | EAC/CPO | Ongoing |  | Participate Frome Nov 2013 and recommendations to be considered | Participate Frome actions continue to be implemented. Volunteer project to be developed to increase volunteer opportunities, volunteer co-ordinator for well being to be supported. To consider further how youth activities engage young people alongside other residents in practical activity in the Town. Pilot project to run with Critchill school and our outside services team. | 503 4723 503 4724
|  | 2.1.4 | Promote community participation | EAC/CPO | 2014/15 | Annual community fair completed 2012, 2013 in planning stage | Participation Week completed Nov 2013 - planning for next steps. Work up plan to deliver Participate Frome recs | Participate Frome actions continue to be implemented: increase and improve communiaction, engage community members actively in projects and issues, continued and increased use of PF branding, increase intergenerational projects. | 503 4723
3. | Enhancing a Thriving Town Centre
| 3.1 | Managing the town centre - change to improving the town centre?
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 3.1.1 | Improve the Town Centre | FC/EDRM | Annual
|  |  | Provide vibrant and sustainable floral planting throughout the year | IAC/EM | Annual |  |  | Florals will focus on town centre and be edible and/or sustainable wherever possible. | 504 4039
|  |  | Explore the introduction of Local Development Orders that will improve the appearance and vitality of the Town Centre (through Neighbourhood Plan) | EAC/PDO | 2014/15 | See 2.3 above |  | Article 4 direction to be applied for to restrict permitted change to uses falling within Use Class A2 to no more than 4% in Badcox/St. Catherine's area (see Neighbourhood Plan TC2) | 506 4129
|  |  | Provide affordable parking in the town | EAC/TCRM | 2014/15 |  | Do not progress | Parking strategy to be drafted winter 2014/15. Implementation thereafter
|  |  | Proactively manage the public realm including notice boards, illegal advertising, the less accessible areas (eg rehabilitation/maintenance of Apple Alley) and street obstructions (eg voluntary codes for A boards) | EAC / TCRM | 2014/15 | Remodelling project |  | Remodelling project - Phases 1 & 2 to be completed 2015/16. New notice boards for suburbs, street cleansing contract to be monitored and enhanced if need be. Apple Alley busniesses will be approached to keep it clean. | EMR 901 9020
|  |  | Develop costed options for remodelling the town centre | EAC/ERDM | 2013/14/15 | On schedule | Palmer St planned for Jan 2014, Boyle Cross planned for 2014. | Palmer St resurfacing to be implemented early 2015; Boyle Cross and crossing points in Market Place to be implemented in 2015/16 | EMR 901 9020
|  | 3.3.6 | Work to ensure empty shops are not an eyesore | EAC/PDO | ongoing |  | Do not progress | Focus to shift to general shopfront improvements within the Market Place, Bath Street & The Bridge and introduction of an Article 4 direction as a way of controlling shopfronts as Phase 3 of Town Centre Remodelling
|  |  | Develop & implement new Implementation Prospectus for Saxonvale | EAC/ERDM |  |  |  | Prospectus commissioned. Implementation will start in early 2015. | EMR 901 9020
|  | 3.3.5 | Encourage County Highways to ensure appropriate resurfacing in and around the town centre | FC/EDRM | 2013/14/15 |  | Palmer street to be resurfaced Jan 2014 and in talks re re-modelling of Mkt Place | Palmer St resurfacing to be implemented early 2015; Boyle Cross and crossing points in Market Place to be implemented in 2015/16 | EMR 901 9020
| 3.2 | Improving the range of shopping facilities
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 3.2.1 | Encourage appropriate developments to enhance the diversity of the shops | EAC/EDRM | 2014/15 |  | Participate Frome rec and planning applications at Saxonvale | Promoted via Saxonvale Implementation Prospectus and via improved team working amoungst businesses facilitated by FTC | 506 4129
|  |  | Build suitable controls into the Town Design Statement and Neighbourhood Development Plan | EAC / PDO | 2014/15 | See 2.3 above |  | See 3.11 above
|  | 3.2.2 | Develop and implement Business Plan to revive the Markets | EAC/ERDM | 2014/15 | See 1.1.1 above | Focus will shift to enhancing Wed/Sat mkt | Strategy to be drafted winter 2014/15. Implementation will contnue through 2015. | EMR 901 9004
|  |  | Investigate possibilities of locally sourced and sustainable produce | EAC/CPO | 2013/14 | New project | Do not progress | Do not progress
| 3.3 | Environmental threshold
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 3.3.1 | Improve cleansing services so that 90% of residents are satisfied | IAC/EM | March 2014 | Resident satisfaction survey planned | Retail surveys carried out, need to analyse results | Retail surveys carried out, need to analyse results. Do not progress residents survey.
|  |  | Consider local provision as part of staffing review | IAC / CE | December 2011 | Completed | Completed | Completed
|  |  | Negotiate SLA's with MDC to take on local cleansing services | IAC /EM | 2013/14 | MDC ground care contract let Oct 2012, in discussion with contractors | Continued pressure on TLG/MDC to deliver contract. Consider buying contract enhancement | Continued pressure on TLG/MDC to deliver contract. Explore supplementing MDC contract with extra TC cleansing | 504 4035
|  |  | Carry out service improvement surveys | IAC /EM | 2014/153 | On schedule | TLG/MDC to do | To be commissioned in March 2016 | 506 4122
|  | 3.3.2 | Review and improve street furniture and signage in the town centre | EAC / TCRM | 2014/15 | In progress - part of N'hood Plan and remodelling project | Cllr Goldfinger to present findings in Feb 2014 | Progress as part of TC remodelling and a focus for the Town Centre Working Party | EMR 901 9020
|  | 3.3.3 | Bid for municipal environmental services i.e. grass cutting, weed control, litter picking, potholes etc | IAC / CE | Summer 2012 | Bid unsuccessful |  | Bid unsuccessful
|  |  | Discuss how improvements can be made with contractor | IAC/EM | 2014/15 | MDC ground care contract let Oct 2012, in discussion with contractors. Lengthsman employed. | Continued pressure on TLG/MDC to deliver contract. Consider buying contract enhancement | Continued pressure on TLG/MDC to deliver contract. Explore supplementing MDC contract with extra TC cleansing | 504 4035
|  | 1.3.1 | Support renewable energy schemes within public and private organisations | EAC / ERO | 2014/15 | Exploring possible hydro project at Welshmill Weir | Continue to work with Converging World | FRECO project up and running. Funding for solar stand at Football Club secured. FRECO will be launching renewable energy projects in 2015 including Frome Medical Practice and additional public and businesses premises wil be explored. | 503 4719
|  |  | Support PV panels for the Cheese & Grain building | FC/CE | 2012/13 | Completed |  | Completed
|  |  | Explore how to facilitate other public buildings to generate renewable energy | EAC/ERO | 2014/15 | New project | Continue to work with Converging World | see above | 503 4719
|  | 3.3.4 | Work in partnership with environmental volunteers i.e. litter picking, river cleansing, education etc | IAC/EM | Ongoing | As and when FTC is approached - Barclays Bank, Friends of River Frome, FROGS all worked with FTC in 2012/13 | Participate Frome litter picks and FoRF river picks supported, | Support FoRF and continue to organise periodic community littter picks. Encourage all schools to adopt a street to keep clean and businesses to keep their frontages clean | 504 4033
|  |  | Work with Frome College to establish a conservation volunteer group | IAC/EM | 2013/14 | New project - dependant on College to progress | Do not progress | see above to start with.
| 3.4 | Freedom of movement around the town centre
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 3.4.1 | Explore how pedestrian accessibility and safety in the town centre can be improved | EAC/EDRM | 2013/14/15 | Part of Market Place Improvements | On schedule | Routes identified, promotion of them is required, this will include between green spaces, housing estates, the railway station and the town centre. | EMR 901 9020
|  | 3.4.2 | Work in partnership with the business and arts community regarding signage as public art | EAC/EDRM | 2013/14 | New project | Do not progress | do not progress
|  | 3.4.4 | Work with the SCC Highways on reducing the travel of heavy goods vehicles through the town | EAC/EDRM | 2013/14 | New project | Do not progress | do not progress
| 3.5 | Built Environment
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 3.5.1 | Survey and evaluate future use of public conveniences |  | December 2011 | Completed |  | Completed
|  |  | Examine other uses for redundant public toilet buildings | EAC/TC | 2013/14 | In discussion with MDC | Not possible to progress | do not progress
|  |  | Work in partnership with MDC on re-use, disposal or demolition of toilet buildings | EAC/TC | 2013/14 | In discussion with MDC | Not possible to progress | do not progress
|  |  | Develop a toilet strategy which is acceptable to the retail sector and improves services to the public | IAC/TCRM | April 2013 | Community Toilet Scheme to start in Apr 2013 | Launched and to be reviewed in 2014 | Relaunched 2014. Needs expansion and improved promotion. | 509 4440
|  | 3.5.2 | Work in partnership with MDC to plant more trees in the Cattle Market car park | IAC/EM | Winter 2012 | MDC won't permit. | Not possible to progress | Redesign and spring clean of Mkt Yard planned for 2015
4. | Ensuring Effective Public and Voluntary Services
| 4.1 | Partnership working to promote Frome needs
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 4.1.1 | Establish a 'Frome Forum' to publicly examine all services across the public sector | FC/TC | 2013/14 | in discussion with mdc | One Frome piloted and not continued | Do not progress
|  | 4.1.2 | Encourage and facilitate a 'Frome Assembly' to bring elected members (across tiers) to account and discuss issues of mutual concern | FC/TC | 2013/14 | First informal meeting held in Dec 2012, | No further progress | Continue to engage with Cllrs from all three tiers of Govt
|  | 4.1.3 | Form excellent relationships with MDC and SCC including through the pathfinder initiative to deliver joint objectives | FC/TC | 2013/14 | Pathfinder project on hold until Mendip hub completed in MDC offices | Frome Hub/move to library in progress | New FTC offices to be third sector hub. Library to be public sector hub | EMR 901 9011
|  | 4.1.4 | Establish an information hub / one stop shop for Frome information | FC/TC | April 2013 | In discussion with scc over poss use of Library | FTC to move to Library in 2014 | Christchurch Street to provide central information point with satelite points. We will improve the diseemination of info virtually and phycally | EMR 901 9011
5. | Ensuring an Innovative and Supporting Town Council
| 5.1 | Rethink the role of the Town Council
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 5.1.1 | Consider the implications of the Localism Act | FC/TC
|  |  | Develop a specific plan for adopting local provisions | FC/TC | 2013/14 | Held seminar on opportunities in June 2012, all Cllr evening in Oct 2012 in order to inform future strategic direction, future discussion planned for Spring 2013 | see below | Do not progress
|  |  | Take a lead on any emerging Department of Communities and Local Government (DCLG) vanguard schemes such as the Neighbourhood Plan and Community Budgeting | FC/TC | 2013/14 | Discussions held and planned with DCLG over community budgeting | Asset of Community Value progressing with FROGS, NP in progress, community budgeting not progressing | monitor development of Localism agenda
|  | 5.1.2 | Review the purpose, role and effectiveness of the Town Council | FC/TC
|  |  | Undertake staff and accommodation review to ensure fit for purpose | FC/TC | May 2012 & 2013/14 | Staff review completed May 2012 and office refurb planned for summer 2013 | Refurb superseded by Library move | Moving to Christchurch Street
|  |  | Ensure that all decisions made by FTC are considered for their sustainability and environmental impact | FC/TC | 2013/14 | Ethical decision making WP due to meet Feb 2013 | Ethical Framework adopted and applied | Ethical Framework adopted and applied
|  |  | Ensure that all decisions made by FTC are considered for their financial, risk, and legal implications | FC/TC | Annual | FTC follows Standing Orders and fin Regs asks for advice from Internal Auditors |  | Review annually and follow Standing Orders and Fin Regs, use Internal Auditors and SLCC for specfic advice | 802 4055 4056
|  |  | Confirm continuing commitment to the Fair Trade movement |  | Ongoing |  |  | Completed
|  |  | Retain FTC's commitment to the 10:10 campaign |  | Ongoing |  |  | Completed
|  |  | Devise strategy to achieve a Carbon Neutral Council | FC/ERO | 2013/14 | New project | New project | Incorporated in all that we do, and specifically in work of sust and recycling officer | 503 4719
|  |  | Carry out service improvement surveys | IAC /TC | 2013/14 | New project | New project | Do not progress | 506 4122
| 5.2 | Promote greater engagement
|  |  | ACTIONS | RESPONSIBLE | TIMESCALE | PROGRESS at Oct 2012 | PROGRESS at Nov 2013 | PROGRESS at Nov 2014 and plan for 2015/16
|  | 5.2.1 | Encourage and make use of local expertise to influence best decisions | FC/TC
|  |  | Develop a skills and interests database | EAC / CPO | March 2014 | In progress | Participate Frome recs database and discussions being held with website developers | Community database exists and needs to be developed further | 802 4027
|  |  | Hold a fair for voluntary, specific interest and community groups to network and share ideas | EAC / CPO | 2014/15 | To be planned for 2013 | Participate Frome week held and now planning to take forward recs | Participate Frome recs being implemented. A Funding Fair to be organised early 2015. Use of Christchurch Street as a pysical and virtual space for increasing engagement | 503 4723 502 4320
|  | 5.2.2 | Improve public participation at formal and informal meetings |  | Ongoing |  | Participate Frome week held and now planning to take forward recs | Continue to explore innovative ways of enabling people to engage in Council meetings | 501 4018
|  |  | Strive to make formal meetings easier for everyone to understand | All / TC | Ongoing | Ongoing |  | as above and trial live twitter postings
|  |  | Make Councillors more accessible to receive and respond to questions and concerns raised by the public | All / TC | Ongoing | Ongoing | More work needed | New notice boards in suburbs providing Cllrs contact details, develop surgeries. Continue to promote contacts on website.
|  |  | Challenge procedures that are barriers to public participation | All / TC | Ongoing | Ongoing |  | on going
|  |  | Consider ways of reaching the wider community by on line or broadcast methods | All / TC | Ongoing | See 1.2.1 above | More work needed via website and other means | Council agreed to any broadcasting of meetings and will trial live twitter feeds | 802 4027
|  | 5.2.3 | Support the young people to genuinely contribute to Council working | All / CPO | 2014/15 | Project needs developing with young people in the town. | Mayor for Yong People appointed. Supporting Youth Council. Youth Services report recs being considered | Youth services project implemented. We will review the way that young people are engaged in the wider community. We will embed youth provision and engagement alongside all community engagement and community group and development support. | 503 4718
KEY
|  | EAC | External Affairs Committee
|  | IAC | Internal Affairs Committee
|  | FC | Full Council
|  | TC | Town Clerk
|  | EM | Envionment Manager
|  | EDRM | Economic Development & Regeneration Manager
|  | RFO | Responsible Finance Officer
|  | PDO | Planning & Development Officer
|  | CPO | Community Projects Officer
|  | ERO | Energy & Recycling Officer
|  | TCRM | Town Centre Regeneration Manager