## Energy 2022 update
Action | Lead Org | Partner orgs | Priority | Update 2022
Work with Planning Authority to look at how retrofit of listed buildings can be supported | FTC | Mendip District Council | High | NEW ACTION
Work with Neighbourhood Networks on energy saving challenge (Transition Streets model) | FTC | Sustainable Frome, Neighbourhood Networks | High | NEW ACTION
Explore a bulk- buying scheme for insulation and heat pumps similar to Solar Streets | FRECO | FTC, Mendip DC | High | NEW ACTION
Link with social housing – Aster, Guinness Trust, Liverty to explore opportunities for retrofit | FTC / Mendip |  | High | Not yet begun
Work with Somerset District Council & Mendip Town Council to commission energy strategy to map renewable energy potential including solar, wind, hydro and anaerobic digestion | FTC | Mendip District Council | High | Not yet begun
Promote retrofit funding available locally such as ECO | FTC |  | High | Ongoing through Healthy Homes project
Train local team of energy advisors / champions | FTC | CSE | High | Ongoing through Healthy Homes project
Explore more opportunities for community owned energy in Frome | FRECO | FTC, Mendip DC | High | Ongoing
Promote CSE Home Energy Helpline | FTC |  | High | Ongoing through Healthy Homes project
Run energy cafes and / or train others such as community connectors and Citizen's Advice to provide information and signpost | FTC |  | High | Ongoing through Healthy Homes project
Promote thermal imaging camera and lend to businesses and schools too | FTC |  | High | Ongoing
Promote solar streets | FTC |  | High | Online Solar Streets event in May 2021 attracted 90 attendees. 30 new installations commissioned; more in progress
Promote free solar for larger buildings via Green Nation | FTC |  | High | Ongoing
Schools campaigns to reduce energy bills, link with Energy Sparks and Salix team at Somerset CC | FTC |  | High | Work with schools put on hold during COVID but FTC are now working with Energy Sparks on a new round of work with schools
Promote checklist for businesses on how to save energy - link with Good Business accreditation | FTC |  | High | Good Business visits postponed throughout COVID but restarted September 2021. So far 3 businesses have received visits.
Develop zero carbon microgrid blueprint at Saxonvale | FTC |  | High | Feasibility study commissioned
Explore linking with Abundance or similar to enable town investment in retrofit, social housing and renewables | FTC / Mendip |  | Medium | Not yet begun
Explore opportunities to train apprentices in energy efficiency and renewables | FTC |  | Medium | Not yet begun
Explore enabling community owned energy to be sold at a reduced rate to local businesses and schools through a corporate PPA structure | FRECo |  | Medium | Ongoing
Ground Source and Air Source Heat Pumps as a planning condition for all new homes | Mendip |  | Medium | Ongoing- included in Frome's planning guidance for the Climate Emergency
Explore local storage opportunities linked to renewables | FTC |  | Medium | Ongoing
Explore opportunities for district heating using renewables in Frome | FTC |  | Medium | Ongoing
Encourage more sharing of properties to reduce energy bills (and housing demand) | Homeshare Mendip |  | Medium | Homeshare Mendip matches match someone who needs a little help to stay living independently in their own home, with someone needing somewhere affordable to live.
Work with local landlords to encourage energy efficiency and empower tenants to take action | FTC | Fair Housing for Frome | Medium | Ongoing. Linking with energy advisers at CSE
Lobby Somerset's Pension Committee to decarbonise our pensions in collaboration with Brunel Pensions Partnership | FTC |  | Medium | Ongoing
Explore & promote finance mechanisms for retrofit, such as low interest loans | FTC | Lendology | Medium | These are provided by Lendology, promoted through Healthy Homes project
Organise Green Open Homes to showcase carbon reduction in local homes |  |  | Medium | Ongoing through Healthy Homes project

## Transport 2022 update
Action | Next step actions - who, what, by when? | Lead Org | Partner 1 | Partner 2 | Partner orgs | Priority | Update 2022
Promote new changes to the Highway Code to support safe walking and cycling. Comms campaign with Pronto |  | FTC/ Pronto |  |  |  | High | NEW ACTION
Enforce & extend 20mph zones |  | FTC |  |  | Community Speedwatch, Somerset CC | High | NEW ACTION
Organise activities to raise profile of cycling in Frome, as there are very few cyclists (1% of journeys on busiest routes) |  | FTC |  |  |  | High | NEW ACTION
secure bike parking in town centre - locked and covered? ebikes are a high value item so locking them in an open space in town is a barrier to using them to get into town |  | FTC |  |  |  | High | NEW ACTION
Support and promote e-cargo bike delivery scheme | FTC |  | High | Not yet completed |  | High | Not yet completed
Map safe walking and cycling routes and key areas that need addressing (Local Cycling and Walking Infrastructure Plan - LCWIP) |  | FTC | Transport Consultant | Somerset CC | Somerset County Council, Mendip DC | High | Ongoing
Promote and organise active travel challenges with local schools including use of Modeshift Stars |  | FTC | Missing Links |  | Public Health England | High | Despite COVID disruption the Active Travel Challenge went ahead with 5 schools in September 2021 | `
Promote paths and walking routes |  | FTC / Walkers Are Welcome |  |  |  | High | Ongoing. Frome has achieved Walkers are Welcome status. Bespoke walking maps avalable from Discover Frome.
Organise bike amnesty, repair, upskilling and cycle confidence classes |  | FTC | Critchill School |  | Edventure (repair centre) | High | Ongoing through Cycle Together scheme
Share and promote cycle maps. National Cycle Network and Local Cycle Network |  | FTC |  |  |  | High | Ongoing
Buy electric bikes to lend on long term hire linking with Medical Practice |  | FTC | Frome Medical Practice |  |  | High | Ongoing through Cycle Together scheme
Promote Co-Wheels hybrid car club | FTC |  | High | Ongoing- third car to be introduced to Frome |  | High | Ongoing- third car to be introduced to Frome
Support and promote Frome’s Missing Links to enable a safe off road cycle path linking Frome with Radstock and Bath |  | FTC | Frome's Missing Link |  | Frome's Missing Links | High | Ongoing
Promote Lift share Frome and support volunteer drivers to enable lift sharing |  | FTC |  |  |  | High | Volunteer drivers provided a critical service throughout COVID. Promotion of Lift Share put on hold for safety.
Promote shared work and school journeys and club – walking / cycling bus |  | FTC |  |  |  | High | To be explored alongside School Streets scheme
Create integrated transport plan for Frome |  | FTC | Local transport Facebook groups | Somerset CC |  | High | Subject to funding/ SCC support
Ensure new developments are designed using the Home Zone concept , keeping cars at the periphery and enabling communities to connect and share car club vehicles. Ensure have walking and cycling links and secure cycle storage |  | FTC | Mendip |  | Mendip DC | High | Climate Emergency Planning Guidance passed September 2021, MDC also passing new SPD
Use electric and hybrid vehicles wherever possible e.g. environment / ranger team's electric van |  | FTC |  |  |  | High | Ongoing- FTC use CoWheels for meetings; rangers have electric vehicles
Totals
Enable communities to bulk buy from local shops and / or ethical organisations like Essential Co-op |  | FTC |  |  |  | Medium | Not yet completed
Explore opportunities for neighbourhood delivery hubs |  | FTC |  |  |  | Medium | Not yet completed
Promote worker incentives such as cycle to work scheme |  | FTC | Love to Ride | Chamber of Commerce |  | Medium | Ongoing
Buy electric bike for council staff use |  | FTC |  |  |  | Medium | Currently staff can use rental bikes FOC for work purposes. Would be good to have a loan scheme as an alternaitive to communiting by car

## Zero Waste 2022 update
Action | Lead Org | Partner orgs | Priority | 2022 update
Host series of Plastic Free and Zero Waste awareness events such as Mass Unwrap, Plastic Free Picnics and educational film screenings. | FTC |  | High | NEW ACTION
Set up reusable nappies scheme | FTC |  | High | NEW ACTION
Promote new recycling services such as the plastic wrapping recycling in Sainsbury's | FTC |  | High | NEW ACTION
Make recycling centre more user friendly. Approach the centre's contractor about how the community could help improve it. Can the centre staff re-sale items that are to good to be recycled on landfilled. | FTC | Somerset Waste Partnership | High | NEW ACTION
Promote Reuse sites such as Freecycle and charities that collect good furniture and electricals | FTC |  | High | NEW ACTION
Work with Mendip and their waste contract to organise annual or bi-annual free bulky waste collection days | FTC | Somerset Waste Partnership | High | NEW ACTION
Work with The Independent Market to be zero waste including exploring food & drink container deposit scheme | FTC | Frome Independent | High | NEW ACTION
Retan Frome's "Plastic Free Communities" status by working with more business and promoting success stories | FTC |  | High | Ongoing
Explore expansion of sharing initiatives such as SHARE, community fridge, Co-Wheels and other share and repair schemes | FTC |  | High | Ongoing
Establish toy library | FTC |  | High | Not yet started
Promote ethical banking, pensions etc | FTC |  | High
Promote neighbourhood sharing through playing out days, neighbourhood sharing hubs, engagement and StreetBank | FTC |  | High | Play Streets trials confirmed for October 2021
Co-organise and promote swishing (clothes swap) and free-cycle days | FTC |  | High | Big Green Clothes Swap held at Silk Mill as part of Great Big Green Week
Link with Frome Medical Practice and work with local schools to provide free re-usable sanitary items and awareness sessions | FTC |  | High | Ongoing. FMP and FTC are linking with Womens Environment Network "environmenstrual" ambassadors and Frome College to organise sessions in schools and create awareness campaign
Explore setting up more community fridges in Frome |  |  | High | Fridge at The Mount run seperately to Frome's Community Fridge, but with coordination & communication between the two. Community Fridge has capacity for more deliveries subject to volunteer & coordinator time
Work with school and hospital catering to source locally, seasonally and increase plant intake | FTC |  | High | FTC commissioned local food network research & held event in September 2021
Look to buy or rent land for local food growing, working in partnership with local forest group | Frome Field to Fork |  | High | FF2F have secured a location and begun work on the land including volunteer days and a Green Gym.
Totals
Explore setting up permanent space for repair | FTC |  | High | Ongoing through Frome Reuse Centre (Edventure project)
Work with schools and others to set up shared food growing spaces | FTC |  | Medium | Not yet started
Explore opportunities for children's shoe library | FTC |  | Medium | Not yet started
Work with local schools and College to organise pre-loved uniform swap events | FTC |  | Medium | Not yet started
Promote repair (and hire) businesses such as Domesticare | FTC |  | Medium | Ongoing
Promote using things for longer and buying quality that lasts e.g. buymeonce website | FTC |  | Medium | Ongoing
Promote charity shop shopping and buying second hand | FTC |  | Medium | Ongoing
Promote Food Hub and other collective places that link with sustainable local production | FTC |  | Medium | Ongoing through Frome Food Network
Enable and promote local food growing training | FTC |  | Medium | Ongoing through Frome Food Network
Promote re-fill / packaging free opportunities like Wholefoods, Oakville Care and Denude | FTC |  | Medium | Ongoing
Promote local food and production and enable / support bulk buying and delivery, explore opportunities for Community Supported Agriculture | FTC |  | Medium | Ongoing through Frome Food Network
Promote food waste apps such as Olio and 2G2G | FTC |  | Medium | Ongoing
Promote farmers markets | FTC |  | Medium | Ongoing
Work with Wells and others to set up local food trail | FTC |  | Medium | Ongoing
Work with businesses to reduce resource use and minimise waste e.g. via Good Business survey and visits | FTC |  | Medium | Ongoing through Good Business Framework

## Biodiversity 2022
Action | Lead Org | Partner orgs | Priority | 2022 update
Develop plan and targets for tree planting | FTC |  | High | Wild About Trees officer delivering a programme of tree planting including planned Tiny Forest project at Egford Park
Support and challenge developers to make new builds more wildlife friendly by including and prioritising things like wildlife corridors, pollinator-friendly planting schemes, ponds, bee-bricks and hedgerows at the design stage | FTC, MDC |  | High | NEW ACTION
Support groups like FORF - and work alongside the EA - to ensure water quality in the river. Including having an effective monitoring and reporting system to enable timely responses to concerns (including discharge into the river) | Friends of the River Frome |  | High | NEW ACTION
Involve residents, visitors and schools in the upcoming Community Wildlife Mapping project; completing surveys to establish biodiversity baselines for the town and its spaces | FTC | SERC | High | Ongoing
Facilitate or encourage conversations with local farmers to discuss restorative and rewilding agriculture among Frome's farming community; also trying to discourage use of pesticides and vary mono-culture | FTC | Mendip DC | High | NEW ACTION
Improved biodiversity in and along the river; following the actions and aims identified in FORF's adopted river strategy | Friends of the River Frome | FTC | High | NEW ACTION
Street trees (and trees in grey spaces) | FTC |  | High | NEW ACTION
Working with the FAA to talk about increased biodiversity in the allotments - and more sustainable and more environmental practices | FTC | Frome Allotments Association | High | NEW ACTION
Signage and interpretation boards to provide information about biodiversity | FTC |  | High | NEW ACTION
Engagement with children and young people re: biodiversity | FTC |  | High | Ongoing
Wider conversation about chemical use, pesticides and insecticides (not just Glyphosate | FTC |  | High | NEW ACTION
Education and engagement generally; explaining what biodiversity is and why it matters | FRTC |  | High | Ongoing
Explore locations that could be rewilded as part of the Wild about Frome project | FTC |  | Medium | Ongoing
Provide homes for wildlife in Frome's green spaces e.g. bird and bat boxes; and hedgehog houses | FTC |  | Medium | Ongoing
Town centre floral displays |  |  | Low
Embracing traditional ways of managing green spaces; scything to cut the grass, for instance |  |  | Low
Protecting swifts as an endangered species |  |  | Low
Start or conversation or provide some information to cat owners about the impact cats can have on wildlife, including birds |  |  | Low

## Completed actions
Energy | Commission energy audit of Town Hall | Internal | FTC | Completed
Energy | Implement energy efficiency recommendations at Town Hall | Internal | FTC | Salix loan obtained for solar panels and LED lighting. As FTH has a new boiler renewable heat is not being considered yet. We are draughtproofing the sash windows in lieu of window upgrades due to the historic nature of the building.
Energy | Lobby for change in national planning guidance, supported by supplementary planning guidance locally. | Planning | FTC / Mendip | Mendip District Council has adopted supplementary planning guidance for the Climate Emergency
Energy | Develop best practice design guidance to incorporate into updated Neighbourhood plan and Mendip Planning rules | Planning | FTC / Mendip | FTC developed and approved Climate Emergency Planning Gudance in Spetember 2021 and is using this to engage Mendip District Council as the Planning Authority to ask them to adopt similar standards. The document has been shared with other Town and Parish Councils in the South West
Energy | Explore opportunities for bulk discount for domestic batteries | Outreach | FTC | Batteries now included in Solar Streets offer
Transport | Buy electric bikes to lend on long term hire linking with Medical Practice | Business | FTC | Ongoing through Cycle Together scheme